## Risks
Risk | Impact(1-5) | Likelihood(1-5) | Severity | Mitigation | Owner | Status | Note
Selector break after Edge upgrade (Chromium) | 4 | 4 | 16 | Use Modern UI Automation with anchors and Object Repository; implement robust waits. | RPA Dev | Clossed
Excel COM interop not available on VM (no Office installed) | 3 | 3 | 9 | Fallback to Workbook activities; feature toggle via Config. | RPA Dev | Open | Not include in test case 1
Orchestrator Assets missing/renamed | 3 | 2 | 6 | Pre-deployment checklist; fail-fast in Init with clear logs; default values in Config. | RPA Lead | Open
Unexpected schema change in input data | 4 | 3 | 12 | Schema-agnostic read; validate columns by name; handle optional columns. | RPA Dev | Open
Network latency or timeout when accessing Orchestrator | 3 | 4 | 12 | Implement retry logic with exponential backoff; monitor Orchestrator health; fail-fast with clear logs | RPA Dev | Clossed